## Summary
Farmers Cooperative Tub Line - Cost to Price
INTERNAL. All costs are MCE budget estimates for review; replace with vendor quotes as they come in.
Area | Cost ($) | Share of cost | Sell at target margin ($) | Proposal price ($) | Margin at proposal
A. Dry ingredients |  |  |  | 275550
B. Molasses |  |  |  | 149200
C. 3-stage cook |  |  |  | 458045
D. Pour turntable |  |  |  | 121400
E. Cure tunnel |  |  |  | 168125
F. Robot and wrap |  |  |  | 207815
G. Controls |  |  |  | 260745
H. Engineering |  |  |  | 104170
I. Start-up services |  |  |  | 13800
Base cost
Contingency |  |  |  | Proposal area prices per MCE-Q-2610-FCO-R1
Total cost with contingency
Proposal sell price (R1)
Gross profit
Gross margin at proposal price
Margin sensitivity
Gross margin | Sell, with robot ($) | Sell, manual stacking ($)
40%
45%
50%
55%
Robot cell cost (tagged 'Robot')
Manual lift-assist station cost instead | 25000 | Assumed lift-assist stacking station cost
Benchmark check
Press tub plant, 2022 sell (3 lines)
Escalated to 2026 dollars
This line's sell as share of benchmark
Schedule (speed to start-up)
Engineering before orders release (wks)
Longest equipment lead time (wks)
Longest-lead item
Installation + commissioning (wks)
Order to start-up (wks)

## Customer ROI
Farmers Cooperative - Make vs Buy ROI
Blue = assumption. Replace buy price and ingredient cost with Farmers Cooperative's actual numbers.
Input | Base case | Conservative | Notes
Line price ($) | 1758850 | 1758850 | Proposal MCE-Q-2610-FCO-R1 sell price
Annual volume (tons) | 5000 | 5000 | Per Jason: ~5,000 tons/yr total
Tub size (lb) | 225 | 225 | 225 lb equivalent tubs
Current buy price per tub ($) | 115 | 100.05 | ASSUMED, mix-weighted (30-13 $115, 38 HI-E $125, 17 +Mag $105); conservative 13% lower
Blended ingredient cost ($/ton) | 458.9 | 504.79 | Finished cost from estimated formulas, mix-weighted 50/25/25; conservative +10%
Tub, lid and label ($/tub) | 14 | 15 | ASSUMED plastic 225 lb tub
Operators on line | 4 | 4 | One shift
Loaded labor rate ($/hr) | 28 | 28 | ASSUMED
Hours per year per operator | 2080 | 2080 | One shift, full year
Energy ($/tub) | 1 | 1.25 | ASSUMED gas + electric
Maintenance (% of line price per yr) | 3% | 3% | ASSUMED
Results
Tubs per year
Ingredients per tub ($)
Labor per tub ($)
Maintenance per tub ($)
Cost to make per tub ($)
Savings per tub vs buying ($)
Annual savings ($)
Simple payback (years)
Simple payback (months)
5-year net savings ($)
Break-even tubs per year
Sources: retail price check - https://nrsworld.com/products/30-13-cooked-plastic-protein-tub ; https://tractorsupply.com/tsc/product/purina-rangeland-30-13-beef-cattle-protein-tub-225-pound-(225-lb)-tub-225-lb

## Inputs
Farmers Cooperative Tub Line - Cost Model Inputs
INTERNAL - MCE cost basis. Blue = editable input. Yellow = key assumption to confirm.
Labor rates ($/hr, burdened cost)
Shop | 65 | Assumed MCE shop fabrication cost rate - confirm
Eng | 95 | Assumed engineering/design cost rate - confirm
Controls | 110 | Assumed controls programming/integration cost rate - confirm
Field | 70 | Assumed field install crew cost rate - confirm
Pricing
Target gross margin | 50% | Per Jason: custom systems priced at 50% margin (sell = 2x cost)
Contingency on cost | 5% | Covers scope growth before FEED fixes the design
Proposal sell price | 1758850 | Proposal MCE-Q-2610-FCO-R1, Oct 20 2026: equipment, engineering, start-up; installation and freight by others
Benchmark: previous press tub plant
2022 sell price (3 press lines) | 1300000 | Per Jason: approx. $1.3M in 2022; 3 press lines
Escalation 2022 to 2026 | 18% | Assumed steel/labor/equipment inflation 2022-2026 - confirm
Schedule (weeks)
FEED + detailed engineering | 8 | Assumed; runs before long-lead orders release
Installation (by others) | 6 | Customer contractor; drives start-up date
Commissioning and training | 2 | Assumed

## Cost Build
Area | Item | Type | Qty | Unit material / buyout ($) | Labor hrs / unit | Labor class | Material ($) | Labor hrs | Labor ($) | Total cost ($) | Lead time (wks) | Option tag | Notes
A. Dry ingredients | Tote unloader frame, hopper and metering screw | Fab | 5 | 6000 | 60 | Shop |  |  |  |  | 10 |  | Example row: MCE-built; qty x unit material + qty x hrs x shop rate
A. Dry ingredients | Load cells and weight controller per unloader | Buyout | 5 | 4000 | 0 | [5 empty] | 4 |  | Loss-in-weight on each tote
A. Dry ingredients | Hoist and trolley per unloader | Buyout | 5 | 3000 | 0 | [5 empty] | 4
A. Dry ingredients | Micro skid feeders (premix + additive) | Buyout | 2 | 12000 | 0 | [5 empty] | 10 |  | Loss-in-weight micro feeders, CPM/Beta Raven or Sudenga class
A. Dry ingredients | Micro skid frame and refill hoppers | Fab | 1 | 5000 | 100 | Shop |  |  |  |  | 8
A. Dry ingredients | Collecting screw conveyor to cook | Fab | 1 | 5000 | 80 | Shop |  |  |  |  | 6
A. Dry ingredients | Dust pickup / bin vent | Buyout | 1 | 8000 | 0 | [5 empty] | 6
B. Molasses | Heated, insulated molasses tank (10-12k gal) | Buyout | 1 | 35000 | 0 | [5 empty] | 12
B. Molasses | Unload and transfer pumps | Buyout | 2 | 7000 | 0 | [5 empty] | 6
B. Molasses | Molasses flow meter | Buyout | 1 | 8000 | 0 | [5 empty] | 8
B. Molasses | Molasses piping, valves, heat tracing | Fab | 1 | 10000 | 120 | Shop |  |  |  |  | 4
C. 3-stage cook | Jacketed auger / mixing conveyor stage (SS304) | Fab | 3 | 18000 | 220 | Shop |  |  |  |  | 14 |  | MCE design; 3 stages
C. 3-stage cook | Gearmotors and drives, cook stages | Buyout | 3 | 4500 | 0 | [5 empty] | 8
C. 3-stage cook | Heat source: packaged hot-oil heater or steam boiler | Buyout | 1 | 65000 | 0 | [5 empty] | 16 |  | Usually the longest lead buyout
C. 3-stage cook | Heating piping and insulation | Fab | 1 | 8000 | 120 | Shop |  |  |  |  | 6
C. 3-stage cook | Vapor vent hood and duct | Fab | 1 | 4000 | 60 | Shop |  |  |  |  | 6
C. 3-stage cook | Platform, stairs and handrail | Fab | 1 | 15000 | 240 | Shop |  |  |  |  | 8
D. Pour turntable | Rotary pour/cure turntable structure | Fab | 1 | 14000 | 260 | Shop |  |  |  |  | 12
D. Pour turntable | Slew bearing and indexing drive | Buyout | 1 | 15000 | 0 | [5 empty] | 12
D. Pour turntable | Pour valve and scale platform | Buyout | 1 | 15000 | 0 | [5 empty] | 8
E. Cure tunnel | Tunnel conveyor, per 10 ft section | Fab | 10 | 2500 | 30 | Shop |  |  |  |  | 10 |  | Qty = tunnel length / 10 ft; length set by cure time in FEED
E. Cure tunnel | Tunnel enclosure panels, per 10 ft section | Fab | 10 | 1200 | 12 | Shop |  |  |  |  | 8 |  | Same qty as conveyor sections
E. Cure tunnel | Supply fans | Buyout | 2 | 5000 | 0 | [5 empty] | 8
E. Cure tunnel | Off-gas exhaust fan and stack | Buyout | 1 | 10000 | 0 | [5 empty] | 8
F. Robot and wrap | Robot palletizer with controller (reman FANUC-class) | Buyout | 1 | 60000 | 0 | [5 empty] | 12 | Robot | New robot adds roughly $30-50k
F. Robot and wrap | End-of-arm tub gripper | Fab | 1 | 6000 | 80 | Shop |  |  |  |  | 6 | Robot
F. Robot and wrap | Robot fence, scanners, safety interlocks | Buyout | 1 | 18000 | 0 | [5 empty] | 6 | Robot
F. Robot and wrap | Semi-automatic stretch wrapper | Buyout | 1 | 15000 | 0 | [5 empty] | 6
G. Controls | PLC, HMI, VFDs and panel hardware | Buyout | 1 | 65000 | 0 | [5 empty] | 12
G. Controls | Control panel build | Labor | 1 | 0 | 250 | Shop |  |  |  |  | 4
G. Controls | PLC/HMI programming and robot integration | Labor | 1 | 0 | 450 | Controls
H. Engineering | Detailed design, drawings and project management | Labor | 1 | 0 | 550 | Eng
I. Start-up services | Start-up services: 1 technician, about 5 days on site | Labor | 1 | 0 | 50 | Controls | [6 empty] | Sold at $13,800 fixed (proposal item 34); installation and freight by others
I. Start-up services | Start-up travel and expenses | Buyout | 1 | 3500 | 0
Total
Legend: blue cells are inputs (qty, unit cost, hours, lead time). Labor class pulls the rate from Inputs. Row 2 is the worked example.